## PMBOK 5th Edition
PMBOK 5th Edition
fnovento@gmail.com
PM Process | PM Sub Process | Knowledge Area | Input | Tools and Techniques | Ouputs
Initiating | Develop Project Charter | Integrated | project statement of work, business case, contract agreeements, EEF, OPA | expert judgment,facilitation techniques | project charter
Initiating | Identify Stakeholders | Stakeholder | project charter, procurement documents, EEF, OPA | stakeholder analysis, expert judgment, meetings | stakeholder register, stakeholder mgmt strategy
Planning | Develop Project Mgmt Plan | Integrated | project charter, outputs from planning other processes, EEF, OPA | expert judgment,facilitation techniques | project management plan
Planning | Plan Scope Mgmt | Scope | project mgmt plan, project charter, EEF, OPA | expert judgment, meetings | Scope mgmt plan, requirements mgmt plan
Planning | Collect Requirements | Scope | scope mgmt plan, requirement mgmt plan, stakeholder mgmt plan, project charter, stakholder register | interviews, focus groups, facilitated workshops, group creativity techniques , group decision making techniques, questionnaires and surveys, observations, prototypes, benchmarking, context diagram, document analysis | requirement documentation, requirement mgmt plan, requirements traceability matrix
Planning | Define Scope | Scope | scope mgmt plan, project charter, requirement documentation, OPA | expert judgment, product analysis, alternatives identification generation, facilitated workshops | project scope statement, project document updates
Planning | Create WBS | Scope | scope mgmt plan, project scope statement, requirement documentation, EEF, OPA | decomposition, expert judgment | WBS, WBS dictionary, scope baseline, project document updates
Planning | Plan Schedule Mgmt | Time | Project mgmt plan, projech charter, EEF, OPA | expert judgment, analytical tecniques, meetings | schedule mgmt plan
Planning | Define Activities | Time | schedule mgmt plan, scope baseline, EEF, OPA | decomposition, rolling wave planning, templates, expert judgment | activity list, activity attributes, milestone list
Planning | Sequence Activities | Time | schedule mgmt plan, activity list, activity attributes, milestone list, project scope statement, EEF,OPA | Precedence diagramming method ( PDM ), dependency determination, applying lead and lags, schedule network templates | project schedule network diagrams, project document updates
Planning | Estimate Activity Resources | Time | schedule mgmt plan, activity list, activity attributes, resources calendars, risk register, activity cost estimates, EEF, OPA | expert judgment, alternative analysis, published estimating data, buttom up estimating, project mgmt software | activity resources requirements, resources breakdown structure, project document updates
Planning | Estimate Activity Duration | Time | schedule mgmt plan, activity list, activity attributes, activity resources requirements, resources calendars, project scope statement, risk register, resource breakdown structure, EEF, OPA | expert judgment, analogous estimating, parametric estimating, three point estimates, reserve analysis | activity duration estimates, project document updates
Planning | Develop Schedule | Time | schedule mgmt plan, activity list, activity attributes, project schedule network diagram, activity resource requirements, resource calendars, activity duration estimates, project scope statement, risk register, project staff assignments, resources breakdown structure, EEF, OPA | schedule network analysis, critical path method, critical chain method, resource leveling optimization techniques, modeling techniques, what if schenario analysis, applying leads and lags, schedule compresssion, scheduling tools | project schedule, schedule baseline, schedule data, project calendar, project mgmt plan updates, project document updates
Planning | Plan Cost Mgmt | Costs | project mgmt plan, project charter, EEF, OPA | expert judgment, analytical techniques, meetings | cost mgmt plan
Planning | Estimate Costs | Costs | cost mgmt plan, scope baseline, project schedule, HR plan, risk register, EEF, OPA | expert judgment, analogous estimating, parametric estimating, bottom up estimating, three point estimates, reserve analysis, cost of quality, project mgmt estimating software, vendor bid analysis, group decision making tecniques | activity cost estimates, basis of estimates, project document updates
Planning | Determine Budget | Costs | cost mgmt plan, activity cost estimates, basis of estimates, scope baseline, project schedule, resource calendars, risk register, contracts Agreements, OPA | cost aggregation, reserve analysis, expert judgment, historical relationships, funding limit reconciliation | cost performance baseline, project funding requirements, project document updates
Planning | Plan Quality Mgmt | Quality | project mgmt plan, scope baseline, stakeholder register, requirements documentation, cost performance baseline, schedule baseline, risk register, EEF, OPA | cost benefit analysis, cost of quality, control charts, seven basic quality tools, benchmarking, design of experiments, statistical sampling, flowcharting, proprietary quality mgmt methodologies, additional quality planning tools, meetings | quality mgmt plan, quality metrics, quality checklists, process improvement plan, project document updates
Planning | Develop Plan HR Mgmt | HR | project mgmt plan, activity resource requirements, EEF, OPA | org charts and position description, networking, organizational theory, expert judgment, meetings | HR mgmt plan
Planning | Plan Communication Mgmt | Communication | project mgmt plan, stakeholder register, stakeholder mgmt strategy, EEF, OPA | communication requirement analysis, communication technology, communication model, communication methods, meetings | communication mgmt plan, project document updates
Planning | Plan Risk Mgmt | Risks | project mgmt plan, project charter, stakeholder register, project scope statement, cost mgmt plan, schedule mgmt plan, communication mgmt plan, EEF, OPA | analytical technicques, expert judgment, meetings, planning meetings and analysis | Risk mgmt plan
Planning | Identify Risks | Risks | risk mgmt plan, activity cost estimates, activity duration estimates, scope baseline, stakeholder register, cost mgmt plan, schedule mgmt plan, quality mgmt plan, project documents, EEF, OPA, HR mgmt plan, scope baseline, stakeholder register, procurement documents | documentation reviews, information gathering techniques, checklist analysis, assumption analysis, diagramming techniques, SWOT analysis, Expert judgment | risk register
Planning | Perform Qualitative Risks Analysis | Risks | risk register, risk mgmt plan, scope baseline, EEF, project scope statement, OPA | risk probability and impact assessment, probability and impact matrix, risk data quality assessment, risk categorization, risk urgency assessment, expert judgment | project documents updates, risk register updates
Planning | Perform Quantitative Risks Analysis | Risks | risk register, risk mgmt plan, cost mgmt plan, schedule mgmt plan, OPA, EEF | data gathering and representation techniques, quantitative risk analysis and modeling tecniques, expert judgment | project document updates, risk register updates
Planning | Plan Risk Response | Risks | risk register, risk mgmt plan | strategies for negative risks or threats, strategies for positive riks or opportunities, contingent response strategies, expert judgment | risk register updates, risk related contract decisions, project mgmt plan updates, project document updates
Planning | Plan Procurements Mgmt | Procurements | project mgmt plan, scope baseline, requirements documentation, teaming aggrements, reisk register, risk related contract decisions, activity resources requirements, project schedule, activity cost estimates, stakeholder register, cost performance baseline, EEF, OPA | make or buy analysis, expert judgment, contract types, market research, meetings | procurement mgmt plan, procurement statements of work, make or buy decisions, procurement documents, source selection criteria, change request, project documents updates
Planning | Plan Stakeholder Mgmt | Stakeholder | project mgmt plan, stakholder register, EEF, OPA | expert judgment, meetings, anlytical techniques | stakeholder mgmt plan, project documents updates
Executing | Direct and Manage Project Execution Work | Integrated | project management plan, approved change requests, EEF, OPA | expert judgment, PMIS, Meetings | deliverables, work performance information data, change requests, project mgmt plan updates, project document updates
Executing | Perform Quality Assurance | Quality | project quality mgmt plan, process improvement plan, quality metrics, work performance information, quality control measurements, project documents | plan quality mgmt and perform quality control tools and techniques, quality audits, process analysis | OPA updates, change requests, project mgmt plan upates, project document updates
Executing | Acquire Project Team | HR | projec HR mgmt plan, EEF, OPA | pre-assignment, negotiation, acquisition, virtual teams, multi criteria decision analysis | project staff assignments, resource calendars, project mgmt plan updates
Executing | Develop Project Team | HR | project staff assignments, project HR mgmt plan, resource calendars | interpersonal skills, training, team building activities, ground rules, co location, recognition and rewards, personnel assesment tools | team performance assessments, EEF updates
Executing | Manage Project Team | HR | project staff assignments, project HR mgmt plan, team performance assessments, issue log, work performance reports, OPA | observation and conversation, project performance appraisals, conflict mgmt, issue log, interpersonal skills | EEF updates, OPA updates, change requests, project mgmt plan updates, project document updates
Executing | Distribute Information Manage Communication | Communication | project communication mgmt plan, work performance reports, OPA, EEF | communication technology, communication models, communication methods, information mgmt systems, performance reporting, information distribution tools | project communications, project mgmt plan, project document updates, OPA updates
Executing | Manage Stakeholder Expectations Engagement | Stakeholder | stakeholder register, stakeholder mgmt strategy plan, communication mgmt plan, project mgmt plan, issue log, change log, OPA | communication methods, interpersonal skills, mgmt skills | issue log, OPA updates, change requests, project mgmt plan updates, project document updates
Executing | Conduct Procurements | Procurements | project procurement mgmt plan, procurement documents, source selection criteria, qualified seller list, seller proposals, project documents, make or buy decisions, teaming agreements, procurement statement of work, OPA | bidder conferences, proposals evaluation techniques, independent estimates, expert judgment, advertising, internet search, analytical techniques, procurement negotiations | selected sellers, procurement contract award, agreements, resource calendars, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Monitor and Control Project Work | Integrated | project mgmt plan, schedule forecasts, validated changes, work performance information, performance reports, EEF, OPA | expert judgment, analytical techniques, PMIS,meetings | change requests, work performance report, project mgmt plan updates, project document updates
Monitoring and Controlling | Perform Integrated Change Control | Integrated | project mgmt plan, work performance information reports, change request, EEF, OPA | expert judgment, meetings, change control meetings tools | approved change request status updates, change log, project mgmt plan updates, project document updates
Monitoring and Controlling | Validate Verify Scope | Scope | project mgmt plan, requirement documentation, requirement traceability matrix, validated deliverables, work performance data | inspection, group decision making techniques | accepted deliverables, change requests, work performance information, project document updates
Monitoring and Controlling | Control Scope | Scope | project mgmt plan, work performance information data, requirement documentation, requirement traceability matrix, OPA | variance analysis | work performance measurements information, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Control Schedule | Time | project mgmt plan, project schedule, work performance information data, project calendars, schedule data, OPA | performance reviews, variance analysis, project mgmt software, resource leveling optimization technique, modeling technique, what if analysis, adjusting leads and lags, schedule compression, scheduling tool | work performance measurements information, schedule forecasts, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Control Costs | Costs | project mgmt plan, project funding requirements, work performance information data, OPA | earned value mgmt, forecasting, to complete performance index, performance reviews,variance analysis, project mgmt software, reserve analysis | work performance measurements information, budget cost forecasts, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Perform Control Quality | Quality | project mgmt plan, quality metrics, quality checklists, work performance measurements data, approved change requests, deliverables, OPA, project documents | seven basic quality tools, cause and effect diagrams, control charts, flowcharting, histogram, pareto chart, run chart, scatter diagram, statistical sampling, inspection, approved change requests review | quality control measurements, validated changes, validated deliverables, work performance information, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Report Performance Control Communication | Communication | project mgmt plan, project communication, issue log, work performance information data, work performance measurements, budget forecasts, OPA | information mgmt systems, expert judgment, meetings , variance analysis, forecasting methods, communication methods, reporting systems | work performance information reports, OPA udpates, change requests, project mgmt plan updates, project documents updates
Monitoring and Controlling | Control Risks | Risks | risk register, project mgmt plan, work performance data information, work performance reports | risk reassessment, risk audits, variance and trend analysis, technical performance measurement, reserve analysis, status meetings | risk register updates, work performance information, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Control Administer Procurements | Procurements | procurement documents, project mgmt plan, contract agreeement , work performance reports, approved change requests, work performance information data | contract change control system, procurement performance reviews, inspection and audits, performance reporting, payment system, claims administration, record mgmt system | work performance information, procurement documentation, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Control Stakeholder Engagement | Stakeholder | project mgmt plan, issue log, work performance data, project documents | information management systems, expert judgment, meetings | work performance information, change requests, project mgmt plan updates, project document updates, OPA updates
Closing | Close Project or Phase | Integrated | project mgmt plan, accepted deliverables, OPA | expert judgment, analytical techniques, meetings | final product, service, or result transition, OPA updates
Closing | Close Procurements | Procurements | project mgmt plan, procurement documentation | procurement audits, procurement negotiations, negotiated settlements, record mgmt system | closed procurements, OPA updates

## PMBOK 4th Edition
PMBOK 4th Edition
fnovento@gmail.com
PM Process | PM Sub Process | Knowledge Area | Input | Tools and Techniques | Ouputs
Initiating | Develop Project Charter | Integrated | project statement of work, business case, contract, EEF, OPA | expert judgment | project charter
Initiating | Identify Stakeholders | Communication | project charter, procurement documents, EEF, OPA | stakeholder analysis, expert judgment | stakeholder register, stakeholder mgmt strategy
Planning | Develop Project Mgmt Plan | Integrated | project charter, outputs from planning processes, EEF, OPA | expert judgment | project management plan
Planning | Collect Requirements | Scope | project charter, stakholder register | interviews, focus groups, facilitated workshops, group creativity techniques , group decision making techniques, questionnaires and surveys, observations, prototypes | requirement documentation, requirement mgmt plan, requirements traceability matrix
Planning | Define Scope | Scope | project charter, requirement documentation, OPA | expert judgment, product analysis, alternatives identification, facilitated workshops | project scope statement, project document updates
Planning | Create WBS | Scope | project scope statement, requirement documentation, OPA | decomposition | WBS, WBS dictionary, scope baseline, project document updates
Planning | Define Activities | Time | scope baseline, EEF, OPA | decomposition, rolling wave planning, templates, expert judgment | activity list, activity attributes, milestone list
Planning | Sequence Activities | Time | activity list, activity attributes, milestone list, project scope statement, OPA | Precedence diagramming method ( PDM ), dependency determination, applying lead and lags, schedule network templates | project schedule network diagrams, project document updates
Planning | Estimate Activity Resources | Time | activity list, activity attributes, resources calendars, EEF, OPA | expert judgment, alternative analysis, published estimating data, buttom up estimating, project mgmt software | activity resources requirements, resources breakdown structure, project document updates
Planning | Estimate Activity Duration | Time | activity list, activity attributes, activity resources requirements, resources calendars, project scope statement, EEF, OPA | expert judgment, analogous estimating, parametric estimating, three point estimates, reserve analysis | activity duration estimates, project document updates
Planning | Develop Schedule | Time | activity list, activity attributes, project schedule network diagram, activity resource requirements, resource calendars, activity duration estimates, project scope statement, EEF, OPA | schedule network analysis, critical path method, critical chain method, resource leveling, what if schenario analysis, applying leads and lags, schedule compresssion, scheduling tools | project schedule, schedule baseline, schedule data, project document updates
Planning | Estimate Costs | Costs | scope baseline, project schedule, HR plan, risk register, EEF, OPA | expert judgment, analogous estimating, parametric estimating, bottom up estimating, three point estimates, reserve analysis, cost of quality, project mgmt estimating software, vendor bid analysis | activity cost estimates, basis of estimates, project document updates
Planning | Determine Budget | Costs | activity cost estimates, basis of estimates, scope baseline, project schedule, resource calendars, contracts, OPA | cost aggregation, reserve analysis, expert judgment, historical relationships, funding limit reconciliation | cost performance baseline, project funding requirements, project document updates
Planning | Plan Quality | Quality | scope baseline, stakeholder register, cost performance baseline, schedule baseline, risk register, EEF, OPA | cost benefit analysis, cost of quality, control charts, benchmarking, design of experiments, statistical sampling, flowcharting, proprietary quality mgmt methodologies, additional quality planning tools | quality mgmt plan, quality metrics, quality checklists, process improvement plan, project document updates
Planning | Develop HR Plan | HR | activity resource requirements, EEF, OPA | org charts and position description, networking, organizational theory | HR plan
Planning | Plan Communication | Communication | stakeholder register, stakeholder mgmt strategy, EEF, OPA | communication requirement analysis, communication technology, communication model, communication methods | communication mgmt plan, project document updates
Planning | Plan Risk Mgmt | Risks | project scope statement, cost mgmt plan, schedule mgmt plan, communication mgmt plan, EEF, OPA | planning meetings and analysis | Risk mgmt plan
Planning | Identify Risks | Risks | risk mgmt plan, activity cost estimates, activity duration estimates, scope baseline, stakeholder register, cost mgmt plan, schedule mgmt plan, quality mgmt plan, project documents, EEF, OPA | documentation reviews, information gathering techniques, checklist analysis, assumption analysis, diagramming techniques, SWOT analysis, Expert judgment | risk register
Planning | Perform Qualitative Risks Analysis | Risks | risk register, risk mgmt plan, project scope statement, OPA | risk probability and impact assessment, probability and impact matrix, risk data quality assessment, risk categorization, risk urgency assessment, expert judgment | risk register updates
Planning | Perform Quantitative Risks Analysis | Risks | risk register, risk mgmt plan, cost mgmt plan, schedule mgmt plan, OPA | data gathering and representation techniques, quantitative risk analysis and modeling tecniques, expert judgment | risk register updates
Planning | Plan Risk Response | Risks | risk register, risk mgmt plan | strategies for negative risks or threats, strategies for positive riks or opportunities, contingent response strategies, expert judgment | risk register updates, risk related contract decisions, project mgmt plan updates, project document updates
Planning | Plan Procurements | Procurements | scope baseline, requirements documentation, teaming aggrements, reisk register, risk related contract decisions, activity resources requirements, project schedule, activity cost estimates, cost performance baseline, EEF, OPA | make or buy analysis, expert judgment, contract types | procurement mgmt plan, procurement statements of work, make or buy decisions, procurement documents, source selection criteria, change request
Executing | Direct and Manage Project Execution | Integrated | project management plan, approved change requests, EEF, OPA | expert judgment, PMIS | deliverables, work performance information, change requests, project mgmt plan updates, project document updates
Executing | Perform Quality Assurance | Quality | project mgmt plan, quality metrics, work performance information, quality control measurements | plan quality and perform quality control tools and techniques, quality audits, process analysis | OPA updates, change requests, project mgmt plan upates, project document updates
Executing | Acquire Project Team | HR | projec mgmt plan, EEF, OPA | pre-assignment, negotiation, acquisition, virtual teams | project staff assignments, resource calendars, project mgmt plan updates
Executing | Develop Project Team | HR | project staff assignments, project mgmt plan, resource calendars | interpersonal skills, training, team building activities, ground rules, co location, recognition and rewards | team performance assessments, EEF updates
Executing | Manage Project Team | HR | project staff assignments, project mgmt plan, team performance assessments, performance reports, OPA | observation and conversation, project performance appraisals, conflict mgmt, issue log, interpersonal skills | EEF updates, OPA updates, change requests, project mgmt plan updates
Executing | Distribute Information | Communication | project mgmt plan, performance reports, OPA | communication methods, information distribution tools | OPA updates
Executing | Manage Stakeholder Expectations | Communication | stakeholder register, stakeholder mgmt strategy, project mgmt plan, issue log, change log, OPA | communication methods, interpersonal skills, mgmt skills | OPA updates, change requests, project mgmt plan updates, project document updates
Executing | Conduct Procurements | Procurements | project mgmt plan, procurement documents, source selection criteria, qualified seller list, seller proposals, project documents, make or buy decisions, teaming agreements, OPA | bidder conferences, proposals evaluation techniques, independent estimates, expert judgment, advertising, internet search, procurement negotiations | selected sellers, procurement contract award, resource calendars, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Monitor and Control Project Work | Integrated | project mgmt plan, performance reports, EEF, OPA | expert judgment | change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Perform Integrated Change Control | Integrated | project mgmt plan, work performance information, change request, EEF, OPA | expert judgment, change control meetings | change request status updates, project mgmt plan updates, project document updates
Monitoring and Controlling | Verify Scope | Scope | project mgmt plan, requirement documentation, requirement traceability matrix, validated deliverables | inspection | accepted deliverables, change requests, project document updates
Monitoring and Controlling | Control Scope | Scope | project mgmt plan, work performance information, requirement documentation, requirement traceability matrix, OPA | variance analysis | work performance measurements, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Control Schedule | Time | project mgmt plan, project schedule, work performance information, OPA | performance reviews, variance analysis, project mgmt software, resource leveling, what if analysis, adjusting leads and lags, schedule compression, scheduling tool | work performance measurements, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Control Costs | Costs | project mgmt plan, project funding requirements, work performance information, OPA | earned value mgmt, forecasting, to complete performance index, performance reviews,variance analysis, project mgmt software | work performance measurements, budget forecasts, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Perform Quality Control | Quality | project mgmt plan, quality metrics, quality checklists, work performance measurements, approved change requests, deliverables, OPA | cause and effect diagrams, control charts, flowcharting, histogram, pareto chart, run chart, scatter diagram, statistical sampling, inspection, approved change requests review | quality control measurements, validated changes, validated deliverables, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Report Performance | Communication | project mgmt plan, work performance information, work performance measurements, budget forecasts, OPA | variance analysis, forecasting methods, communication methods, reporting systems | performance reports, OPA udpates, change requests
Monitoring and Controlling | Monitor and Control Risks | Risks | risk register, project mgmt plan, work performance information, performance reports | risk reassessment, risk audits, variance and trend analysis, technical performance measurement, reserve analysis, status meetings | risk register updates, OPA updates, change requests, project mgmt plan updates, project document updates
Monitoring and Controlling | Administer Procurements | Procurements | procurement documents, project mgmt plan, contract, performance reports, approved change requests, work performance information | contract change control system, procurement performance reviews, inspection and audits, performance reporting, payment system, claims administration, record mgmt system | procurement documentation, OPA updates, change requests, project mgmt plan updates
Closing | Close Project or Phase | Integrated | project mgmt plan, accepted deliverables, OPA | expert judgment | final product, service, or result transition, OPA updates
Closing | Close Procurements | Procurements | project mgmt plan, procurement documentation | procurement audits, negotiated settlements, record mgmt system | closed procurements, OPA updates